## New Trail Construction Plan
SMBA Operating Plan 2020-2024
New Trail Construction Projects
Proposed Trail | Operating Year | Caveats to Implementation | Mapping Accuracy | Trail Objective(s) | Trail Description | Construction Plan | Estimated Cost/M | Estimated Cost
Bluff Expansion Project Phase 2 | 2020 | Funding | High | Create intermediate trail opportunities that include progressive features so that all riding abilities can maximize enjoyment of the trail | Section 2: 2.6KM New two-way intermediate trail along the dry pine ridge that climbs up towards the end of Nervous Shakedown to the north. Includes upgrades to existing skid trail to manage water. | Machine built with hand shaping of trail features and final tread. | 18 | 20800
| 2020 | Adequate Layout | Medium | Provide new downhill trail opportunities with more jumps and features; | New downhill trail with TTF's from the mid point of the new Deep Bluff trail down towards Back in Black. | Hand built via Brigade | NA | NA
| 2020 |  | High |  | New trail connecting the Broken Axe (just above the Remeberance Day start) to the beginning of Skizo. Trail will be all mountain style with a few TTF's. | Hand built via Brigade | NA | NA
| 2021 | Adequate Layout | Low |  | New machine built trail that extends off the newly built Deep Bluff trail to trend east toward Seymour Ridget, then turns west and downhill through the clearcut and connects to the new Daly Creek Bridge. Trail will be flow style with jumps, small gaps, rock drops and berms throughout. | Contracted build via NDIT and SMBA | $25/m | 35000
Hudson Bay Mountain Trail - Phase 1 | 2021 | Funding, Capacity | High | 1. Increase destination trail availability in Smithers; | Section 1: 7.4KM - New trail from the Prairie T-Bar parking area for intermediate climbing toward Crater Lake. | Machine built up track to Crater Lake. Intermediate trail rating. Trail will flow both ways. | 25 | 185000
|  | Funding, Capacity |  |  | Section 2: 1.2KM - New section of advanced trail with advanced features that would initiate off the new Crater Lake climbing trail and extend the existing Backdoor Trail. | Backdoor extension will be hand built with advanced features. | 24 | 28800
Hudson Bay Mountain Trail - Phase 2 | 2022 | Funding, Capacity | Medium | 2. Increase bike packing and adventure biking opportunities in Smithers | Section 3: 5.6KM - Two way trail to connect from Crater Lake through dry pine forest with rock features to connect to existing trail that end up at the start off the Silvern Lake trail. | Machine/Hand Build | 24 | 134400
|  | Funding, Capacity |  |  | Section 4: 6.6KM - Upgrades of existing Silvern Lake Trail with some minor re-route through steep and technical sections ending at Lower Silvern Lake. | Machine/Hand Build | 24 | 158400
Hudson Bay Mountain Trail - Phase 3 | 2023 | Funding, Capacity | Medium | 3. Increase access to alpine and backcountry camping access via mountain bike. | Section 5: 6.8KM - Climb out of Upper Silvern Lake and connect into existing road system to gain access into Schufer Lake.. After the lake lien would navigate though technical terrain downhill to connect into Toboggan Creek Road. | Machine/Hand Build | 24 | 163200
Nervous Shakedown to Sidewinder Road | 2022 | Adequate Layout | Low | 1. Increase connectivity between the Bluff Trail Network to Backdoor and future opportunities on the ski hill. | 2.2KM - Previous reconnaissance indicates the potential for a trail that utilizes existing road to connect the top of the Nervous Shakedown decent with the Sidewinder Road on the ski hill to create connectivity to Backdoor area | Hand built 2-way trail, with advanced natural features. | NA | NA
|  | Adequate Layout |  | 2. Increase two way trail opportunities and increase the connectivity within the Bluff network.
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We need a champion for this work. I can help support getting grants etc. but cannot be the one leading the charge.

## Trail Feature Enhancement Plan
Existing Trail Enhancement Projects
Trail | Description | Mapping Accuracy | Construction Plan | Estimated Cost
Four Horseman | New jumps right after Bluff x-ing in the rock section. | High | Brigade/AAT
Huck'in Eh | Dirt works, corners, tightening | High | Brigade/AAT
Shining | Re-build Red Rum drop | High | Brigade/AAT | 500
Shining | Re-build A-frame structure that was removed in 2019. | High | Brigade/AAT | 500
Deep Bluff (Section 1 - New trail) | Improve and add new features. Improve drainage | High | Contractor - Pending funding | 5000
Deep Bluff (Section 3 - New trail) | Drainage, compaction, fix ruts | High | Contractor - Pending funding | 5000
Cronin | Brush up to park boundary | High | Contractor - Pending funding | 5000

## Trail Maintenance Plan
Trail Name | Trail Objective(s) | Special Maintenance Priorities | Construction Plan
All Screwed Up | 1
Apocalypse | 2
Aunti Flo | 1
Back in Black | 1 & 2 | Minor enhancements & 2-3 jumps | Brigade/AAT
Boardwalk | 1 | Replace decking as needed | Brigade/AAT
Broken Axe | 1 & 2 | Repair tread from stumps, danger tree falling | Brigade/AAT
Child's Play | 1
Four Horseman | 1 & 2 | New jumps | Brigade/AAT
Long way | 1
Meanstreak | 1 & 2 | Incrementally improve ridability on the loop section to create similar trail experience throughout. | Brigade/AAT
Nervous Shakedown | 1 & 2 | Add jumps to main downhill explore other terrain adjacent to line. | Brigade/AAT
Penetralia | 1 | Begin discussion on shifting to Objective 3 | Brigade/AAT
Q connector | 1
Remembrance Day | 1 & 2 | Continue modernization started in 2019 | Brigade/AAT
Shining | 1 & 2 | Rake rocks off tread, build large jump next to original and remove camber from transition, improve corner into Apocalypse | Brigade/AAT
Skitzo | 1 & 2
Smoothy | 1
Soul Stripper | 1
Stiff Upper Lip | 1
Upper Bluff | 1
Upper Longway | 1
Upper Remembrance Day | 1 & 2 | Modernize while maintaining existing line. | Brigade/AAT
Uptrack | 1
Huckin' Eh | 1 & 2 | Maintain lips and enhance trail as needed (akin to 2018 works) | Paid/AAT
Pump Daddy | 1 & 2
Pay Dirt | 1 | Fix drainage issues, rake rocks off tread, generally revitalize/restore, and brush | Paid/AAT
Piper Cross | 1
Piper Down | 1 & 2 | Revitalize, restore, and brush | Paid/AAT
Back Door | 1 | Bridge replacement | Paid/AAT
Trail Objectives: |  | ALL Trails in 2020
1. Maintain trail in existing condition and manage for sustainability |  | Remove trees as needed, manage deadfall | Paid/Brigade/AAT
2. Maintain the trail through incremental enhancements that improve ride quality; |  | Manage all drainages | Paid/Brigade/AAT
3. Re-work trail to improve sustainability and ridability |  | Improve signage | SMBA Exec